# Financial proposal: Strengthening Investor Relations in Ethiopia's Capital Market

FSD Ethiopia and the Ethiopian Securities Exchange | Submitted separately from the technical proposal | 2 October 2026

The total estimated budget is USD 92,188 before tax: USD 72,788 in professional fees for 285 consultant days and USD 19,400 in reimbursable expenses. This follows the Annex 1 template, with one column for each of the eight deliverables.

## Fees

| Title / role | Daily rate (USD) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | Days | Fees (USD) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Team Lead, Investor Relations and Capital Markets Expert [to be confirmed] | 450 | 5 | 6 | 3 | 8 | 3 | 3 | 5 | 3 | 36 | 16,200 |
| Engagement Director; investor engagement lead (Regina Love Clarkson) | 190 | 3 | 2 | 1 | 3 | 3 | 2 | 10 | 3 | 27 | 5,130 |
| Disclosure, Governance and Regulatory Expert [to be confirmed] | 350 | 4 | 10 | 1 | 3 | 0 | 3 | 2 | 1 | 24 | 8,400 |
| Training and Capacity-Building Specialist [to be confirmed] | 400 | 2 | 4 | 10 | 16 | 0 | 0 | 0 | 2 | 34 | 13,600 |
| Local Market Specialist [to be confirmed] | 250 | 6 | 4 | 2 | 10 | 3 | 3 | 5 | 2 | 35 | 8,750 |
| ESG and Inclusive Finance Expert (Caroline N. Ndegwa) | 140 | 3 | 8 | 1 | 3 | 0 | 3 | 2 | 1 | 21 | 2,940 |
| ESG disclosure standards (Dr. Perihan Abdelghaly) | 215 | 1 | 5 | 0 | 0 | 0 | 4 | 0 | 0 | 10 | 2,150 |
| Scorecard methodology and data (Caroline McCoy) | 198 | 2 | 0 | 0 | 0 | 2 | 10 | 6 | 1 | 21 | 4,158 |
| Project manager (Boisy V.A. Williams) | 230 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 6 | 23 | 5,290 |
| Toolkit and report design (Damilare Jegede) | 120 | 0 | 8 | 5 | 4 | 0 | 2 | 2 | 2 | 23 | 2,760 |
| Coordination, tracker and data (Anastasia Muthoni) | 110 | 3 | 4 | 3 | 6 | 3 | 4 | 3 | 5 | 31 | 3,410 |
| Total days |  | 32 | 53 | 28 | 56 | 16 | 36 | 38 | 26 | 285 |  |
| Fees by deliverable (USD) |  | 8,571 | 13,235 | 7,920 | 16,370 | 3,856 | 7,930 | 8,828 | 6,078 |  | 72,788 |

Deliverables: D1 Inception report and diagnostic assessment; D2 Investor relations toolkit, draft and final; D3 Workshop design pack; D4 Workshops delivered and training evaluation report; D5 Investor relations society or platform framework; D6 Industry recognition and performance scorecard design; D7 ESX investor relations and investor engagement strategy; D8 Final assignment report and handover package.

## Reimbursable expenses

| Description | Unit cost (USD) | Quantity | Amount (USD) |
| --- | --- | --- | --- |
| Return international flights to Addis Ababa | 700 | 6 trips | 4,200 |
| Accommodation and per diem in Addis Ababa | 150 | 30 nights | 4,500 |
| Local transport in Addis Ababa | 40 | 40 days | 1,600 |
| Visas and travel insurance | 100 | 6 trips | 600 |
| Workshop venue, refreshments and printing (three two-day workshops, up to 30 participants each) | 2,000 | 3 workshops | 6,000 |
| Amharic interpretation and translation of toolkit templates | 2,500 | 1 | 2,500 |
| Total reimbursable expenses |  |  | 19,400 |

## Summary

| Item | Amount (USD) |
| --- | --- |
| Professional fees | 72,788 |
| Reimbursable expenses | 19,400 |
| Total fees and expenses, before tax | 92,188 |
| Tax | Withheld at source by FSD Ethiopia at the applicable rate, as Section 13 of the terms of reference provides |

## Value for money

We have built the budget on the four principles of value for money. Economy: rates are set against each expert’s role and experience, and the team mix keeps senior time on the work that needs it. Efficiency: we adapt tested toolkits from peer exchanges instead of building from scratch, which keeps design days low and puts more time into fitting the content to Ethiopia. Effectiveness: 56 of the 285 days go to delivering and evaluating the workshops, and another 53 to the toolkit, the two outputs participants use directly. Equity: a local market specialist is on the team for 35 days, and the toolkit and workshops address gender and inclusion in disclosure.

## Assumptions and terms

- Three two-day workshops in Addis Ababa, with up to 30 participants each. If ESX provides the venue, the venue line reduces.

- Economy-class travel; accommodation and per diem at the unit costs above. Expenses are billed at actual cost up to the amounts shown.

- One consultant day equals eight productive hours. Prices are in US dollars and held firm for the three-month assignment.

- FSD Ethiopia and ESX return comments on drafts within five working days.

- This financial proposal is valid for 90 days from the submission date.

Proposed payment against deliverables

| Milestone | Share of total |
| --- | --- |
| Deliverable 1, inception report, accepted | 15% |
| Deliverable 2, final toolkit, accepted | 20% |
| Deliverables 3 and 4, workshops delivered and evaluation report, accepted | 25% |
| Deliverables 5 and 6, society framework and recognition and scorecard design, accepted | 15% |
| Deliverable 7, ESX strategy, accepted | 15% |
| Deliverable 8, final report and handover, accepted | 10% |